## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US01 | As a user, I want to create a project so that I can maintain project information in one workspace. | Must Have | Project API | Megha Paramanand Hiremath | Completed
Sprint 1 | Sprint 1 | US02 | As a user, I want to view all projects so that I can select the project I want to work on. | Must Have | Project API | Megha Paramanand Hiremath | Completed
Sprint 1 | Sprint 1 | US03 | As a user, I want to search projects by title or description so that I can quickly find a project. | Must Have | Project Listing | Megha Paramanand Hiremath | Completed
Sprint 2 | Sprint 2 | US04 | As a user, I want to upload multi-format documents so that project information can be processed. | Must Have | Ingestion Pipeline | Megha Paramanand Hiremath | Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 24 | 4 | 5 | 4 | 0 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US01 | S1-T01 | Implement create-project API and validation | 31-Aug-26 | 31-Aug-26 | Megha Paramanad Hiremath | Development | Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US02 | S1-T02 | Implement project listing and project card details | 31-Aug-26 | 01-Sep-26 | Megha Paramanad Hiremath | Development | Completed | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US03 | S1-T03 | Implement project title and description search | 01-Sep-26 | 02-Sep-26 | Megha Paramanad Hiremath | Development | Completed | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US04 | S2-T01 | Implement PDF, DOCX, TXT and CSV ingestion | 03-Sep-26 | 04-Sep-26 | Megha Paramanad Hiremath | Development | Completed | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US05 | S2-T02 | Implement cleaning and document chunking | 04-Sep-26 | 05-Sep-26 | Megha Paramanad Hiremath | Development | Completed | 5 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Project creation validation needed additional checking. | Added required-field validation and tested valid and invalid project details.
Sprint 1 | Day 2 | Project search needed to support both title and description. | Updated filtering logic and verified search with multiple keywords.
Sprint 2 | Day 5 | Different document formats required separate parsing checks. | Tested PDF, DOCX, TXT and CSV ingestion independently.
Sprint 2 | Day 7 | Embedding and vector storage needed retrieval verification. | Performed semantic search tests using stored document chunks.
Sprint 3 | Day 9 | Workspace data refresh required validation after document upload. | Updated refresh flow and verified document information on the workspace.
Sprint 3 | Day 12 | Negative RAG cases required additional validation. | Added unavailable-information handling and completed end-to-end tests.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 31-Aug-26 | 02-Sep-26 | Megha Paramanad Hiremath | Start testing project creation and search immediately after implementation. | Stop assuming that successful form submission means the data is correct. | Continue maintaining clear project and task information. | Added validation and unit tests for project creation, listing and search.
2 | Sprint 2 | 03-Sep-26 | 06-Sep-26 | Megha Paramanad Hiremath | Start testing every supported document format separately. | Stop delaying ingestion and retrieval testing until the end of the sprint. | Continue modular development of ingestion, processing and vector services. | Added format-specific tests and verified document processing through vector storage.
3 | Sprint 3 | 07-Sep-26 | 10-Sep-26 | Megha Paramanad Hiremath | Start regression testing after every defect fix. | Stop ignoring negative retrieval and unavailable-information scenarios. | Continue documenting defects and testing the complete user workflow. | Completed workspace integration, semantic retrieval, negative tests and end-to-end testing.